## RAID Log
ID | Type | Risk / Assumption / Issue / Dependency | Impact | Likelihood | Severity | Mitigation / Response | Owner | Status | Phase / Disposition | BA-16 Final Disposition
R1 | Risk | Severe class imbalance may reduce usefulness of accuracy. | High | High | High | Use recall, precision, F1, ROC-AUC, cost-sensitive evaluation and threshold tuning. | Data/Analytics | Open | Proof of concept | Accepted risk – monitor
R2 | Risk | Truck proxy may not represent marine/offshore failure behaviour. | High | High | High | Treat as proof of concept; validate on governed CGSL data before production. | Project Sponsor | Open | Proof of concept | Accepted limitation – production validation required
R3 | Risk | False negatives may miss consequential failures. | High | Medium | High | Conservative thresholding, cost-sensitive evaluation and human review for high-consequence cases. | Technical/HSE | Open | Proof of concept | Mitigated for prototype; retain for production
R4 | Risk | Privacy exposure may occur when CGSL data is introduced. | High | Medium | High | Data minimization, RBAC, encryption, retention controls and audit logging. | Compliance/IT | Open | Production readiness | Open – implement before CGSL data ingestion
R5 | Risk | Model or data drift may reduce performance over time. | Medium | Medium | Medium | Monitor performance and data distributions; retrain through controlled approval. | Data/Analytics | Open | Production readiness | Open – ongoing monitoring required
R6 | Risk | Automation bias may cause users to over-trust recommendations. | High | Medium | High | Display limitations and explanations; require qualified human approval. | Governance Team | Open | Production readiness | Open – human approval control required
A1 | Assumption | Approved access will be available to the public proxy and, later, authorized CGSL data. | Medium | Medium | Medium | Confirm data-access and ownership requirements before production phase. | Project Sponsor | Open | Production readiness | Assumption to validate
A2 | Assumption | Technical and HSE reviewers will be available for model review. | Medium | Medium | Medium | Schedule review gates within each sprint. | Project Manager | Open | Production readiness | Assumption to validate
I1 | Issue | Public dataset contains anonymized variables and missing values. | Medium | High | Medium | Create data dictionary at group level and document limitations; profile missingness before modelling. | Data/Analytics | Open | Proof of concept | Documented and accepted
I2 | Issue | The proof-of-concept cannot claim CGSL-specific failure rates. | High | High | High | Use explicit proxy disclaimer throughout report and dashboard. | Project Sponsor | Open | Proof of concept | Documented limitation
D1 | Dependency | Future production validation depends on CGSL vessel/equipment/maintenance data. | High | Medium | High | Define target schema and data-readiness checklist before production pilot. | Data/Business Analysts | Open | Production readiness | Open – data readiness gate
D2 | Dependency | Power BI/Azure access is required for a production-style implementation. | Medium | Medium | Medium | Use local development for proof of concept; confirm enterprise access before deployment. | IT/Data | Open | Production readiness | Open – enterprise platform dependency

## BA-16 Tracker
BAN6800 Module 2 – BA-16 Completion Tracker
Ticket | Workstream | Status | Evidence | Key output | Next action
BA-01 | Repository / structure | Done | GitHub repository | Repo structure and baseline documentation | None
BA-02 | Public proxy dataset | Done | data/raw + provenance README | UCI APS training/test/description files | Replace/augment with governed CGSL data in production
BA-03 | Data dictionary | Done | data/data_dictionary/Preliminary_Data_Dictionary.xlsx | 171 fields documented individually | Expand with CGSL field definitions
BA-04 | Data understanding | Done | notebooks/01_data_understanding.ipynb + BA-04 reports | Profiling, imbalance and data-quality summary | Re-run against CGSL data
BA-05 | Preprocessing | Done | notebooks/02_data_preparation.ipynb + processed arrays | Median imputation + missingness handling | Validate with production schema
BA-06 | EDA | Done | notebooks/03_exploratory_analysis.ipynb + BA-06 summary | Distribution, group differences and screening | Confirm domain relevance on CGSL data
BA-07 | Feature engineering | Done | notebooks/04_feature_engineering.ipynb + mapping | 334 retained features after zero-variance removal | Review feature stability on CGSL data
BA-08 | Baseline classifier | Done | notebooks/04_model_development_BA-08.ipynb + report | Logistic regression baseline | Retain as benchmark
BA-09 | Classifier comparison | Done | notebooks/05_classifier_comparison_BA-09.ipynb + report | Random Forest provisional winner | Validate on production data
BA-10 | Cost-sensitive threshold | Done | notebooks/06_threshold_cost_sensitive_BA-10.ipynb + report | Selected threshold 0.10; 74.96% internal cost reduction | Recalibrate with actual CGSL costs
BA-11 | Model documentation | Done | Model card + evaluation report | Model limitations, method and evaluation documented | Update with production evidence
BA-12 | Risk ranking | Done | notebooks/07_risk_ranking_BA-12.ipynb + ranking outputs | 16,000 proxy observations ranked by risk | Use real CGSL asset IDs in production
BA-13 | Prescriptive rules | Done | Decision matrix + recommendations | Risk-to-action mapping with human approval | Calibrate maintenance actions with SMEs
BA-14 | Power BI dashboard | Done | 3 page screenshots + supporting datasets | Executive, action queue and decision support views | Connect to governed CGSL data
BA-15 | Privacy/fairness/explainability | Done | Governance document + checklists | Controls, monitoring and explanation plan | Execute controls before production
BA-16 | RAID / final documentation | In Progress | This package | Final tracker, RAID updates, handover and evidence index | Upload to GitHub and close ticket

## BA-16 Summary
BA-16 Executive Summary
Measure | Value
Project scope | AI-enabled predictive and prescriptive analytics for marine asset maintenance and operational availability at CGSL
Public proxy | UCI APS Failure at Scania Trucks dataset
Training / test observations | 60,000 / 16,000
Final feature count | 334
Selected model | Random Forest
Selected alert threshold | 0.10
Critical threshold | 0.50
BA-10 Internal Evaluation
Metric | Threshold 0.50 | Selected 0.10 | Interpretation
Precision | 0.828 | 0.3621 | Lower at selected threshold; more alerts are accepted to reduce false negatives.
Recall | 0.65 | 0.945 | Substantially higher recall at selected threshold.
F1 | 0.7283 | 0.5235 | Trade-off accepted under the proxy cost structure.
Estimated cost | 35270 | 8830 | 74.96% internal cost reduction relative to 0.50 threshold.
ROC-AUC | 0.9811 | 0.9811 | Threshold-independent discrimination metric on the internal evaluation split.