## RAID Log
ID | Type | Risk / Assumption / Issue / Dependency | Impact | Likelihood | Severity | Mitigation / Response | Owner | Status
R1 | Risk | Severe class imbalance may reduce usefulness of accuracy. | High | High | High | Use recall, precision, F1, ROC-AUC, cost-sensitive evaluation and threshold tuning. | Data/Analytics | Open
R2 | Risk | Truck proxy may not represent marine/offshore failure behaviour. | High | High | High | Treat as proof of concept; validate on governed CGSL data before production. | Project Sponsor | Open
R3 | Risk | False negatives may miss consequential failures. | High | Medium | High | Conservative thresholding, cost-sensitive evaluation and human review for high-consequence cases. | Technical/HSE | Open
R4 | Risk | Privacy exposure may occur when CGSL data is introduced. | High | Medium | High | Data minimization, RBAC, encryption, retention controls and audit logging. | Compliance/IT | Open
R5 | Risk | Model or data drift may reduce performance over time. | Medium | Medium | Medium | Monitor performance and data distributions; retrain through controlled approval. | Data/Analytics | Open
R6 | Risk | Automation bias may cause users to over-trust recommendations. | High | Medium | High | Display limitations and explanations; require qualified human approval. | Governance Team | Open
A1 | Assumption | Approved access will be available to the public proxy and, later, authorized CGSL data. | Medium | Medium | Medium | Confirm data-access and ownership requirements before production phase. | Project Sponsor | Open
A2 | Assumption | Technical and HSE reviewers will be available for model review. | Medium | Medium | Medium | Schedule review gates within each sprint. | Project Manager | Open
I1 | Issue | Public dataset contains anonymized variables and missing values. | Medium | High | Medium | Create data dictionary at group level and document limitations; profile missingness before modelling. | Data/Analytics | Open
I2 | Issue | The proof-of-concept cannot claim CGSL-specific failure rates. | High | High | High | Use explicit proxy disclaimer throughout report and dashboard. | Project Sponsor | Open
D1 | Dependency | Future production validation depends on CGSL vessel/equipment/maintenance data. | High | Medium | High | Define target schema and data-readiness checklist before production pilot. | Data/Business Analysts | Open
D2 | Dependency | Power BI/Azure access is required for a production-style implementation. | Medium | Medium | Medium | Use local development for proof of concept; confirm enterprise access before deployment. | IT/Data | Open